## Final Assigment_v3
ID | Name | Begin date | End date | Duration | Completion | Cost | Coordinator | Predecessors | Outline number | Resources | Web Link | Notes
1 | Opsstart | 24.04.17 | 29.05.17 | 26 | 0 | 9150 |  |  | 1
2374 | Upstarts documents and setup cordenation channels | 12.05.17 | 29.05.17 | 12 | 0 | 2200 | Jared |  | 1.1 | Jared
2405 | SWAT diagram | 12.05.17 | 29.05.17 | 12 | 0 | 0 |  |  | 1.1.1
2408 | Copy_Figure out hosting | 18.05.17 | 29.05.17 | 8 | 0 | 1000 | Jared | 177 | 1.1.2 | Jared
38 | Project Scoope and Vision | 24.04.17 | 09.05.17 | 12 | 0 | 1312.5 |  |  | 1.2
39 | First meeting with customur | 24.04.17 | 24.04.17 | 0 | 0 | 0 | Jared |  | 1.2.1 | Jared
40 | Strategy | 25.04.17 | 03.05.17 | 7 | 0 | 1312.5 |  |  | 1.2.2
41 | Target audience | 25.04.17 | 27.04.17 | 3 | 0 | 562.5 | Jared |  | 1.2.2.1 | Jared
42 | Customer personas | 28.04.17 | 01.05.17 | 2 | 0 | 375 | Jared | 41 | 1.2.2.2 | Jared
43 | Customer journey | 02.05.17 | 03.05.17 | 2 | 0 | 375 | Jared | 42 | 1.2.2.3 | Jared
44 | Scoop and Vison Agreement Meeting | 10.05.17 | 10.05.17 | 0 | 0 | 0 | Jared |  | 1.2.3 | Jared
146 | Create scope and agreement document | 04.05.17 | 09.05.17 | 4 | 0 | 0 |  | 40 | 1.2.4
4 | Assemble team | 24.04.17 | 29.05.17 | 26 | 0 | 2687.5 |  |  | 1.3
175 | Hiring advertisments | 24.04.17 | 25.04.17 | 2 | 0 | 250 | Jared |  | 1.3.1 | Jared
6 | Interviews | 26.04.17 | 22.05.17 | 19 | 0 | 1187.5 | Jared | 175 | 1.3.2 | Jared
49 | Hireing contracts and papir | 23.05.17 | 29.05.17 | 5 | 0 | 1250 | Jared | 6;177 | 1.3.3 | Jared
177 | Setup the budget | 10.05.17 | 17.05.17 | 6 | 0 | 2700 | Jared |  | 1.4 | Jared;Clark
150 | Figure out hosting | 18.05.17 | 19.05.17 | 2 | 0 | 250 | Jared | 177 | 1.5 | Jared
2300 | Project statues and Buget | 17.08.17 | 04.09.17 | 13 | 0 | 5675 |  |  | 2
2302 | Project inventory | 17.08.17 | 22.08.17 | 4 | 0 | 500 | Jared |  | 2.1 | Jared
2304 | Buget review | 23.08.17 | 04.09.17 | 9 | 0 | 5175 | Jared | 2302 | 2.2 | Jared;Clark
2373 | Statues meeting with customur | 05.09.17 | 05.09.17 | 0 | 0 | 0 | Jared |  | 2.3 | Jared;Clark
201 | Webpage development | 22.05.17 | 07.11.17 | 122 | 0 | 31075 | Jared |  | 3 | Jared
1300 | Webpage development startup | 22.05.17 | 01.06.17 | 9 | 0 | 2025 | Jared |  | 3.1 | Jared
1301 | Platform/technology Research and Prototypes | 25.05.17 | 01.06.17 | 6 | 0 | 1200 | Webster |  | 3.1.1 | Webster
1302 | Setup development enviroment | 22.05.17 | 24.05.17 | 3 | 0 | 600 | Webster |  | 3.1.2 | Webster
1305 | Page Structure | 02.06.17 | 20.06.17 | 13 | 0 | 3050 | Jared |  | 3.2 | Jared
1314 | User Testing - Page Structure | 05.06.17 | 19.06.17 | 11 | 0 | 125 |  |  | 3.2.1
1315 | test page structure | 05.06.17 | 05.06.17 | 1 | 0 | 25 | Jared |  | 3.2.1.1 | Jared
1316 | test page structure | 12.06.17 | 12.06.17 | 1 | 0 | 25 | Jared |  | 3.2.1.2 | Jared
1317 | final test page structure | 19.06.17 | 19.06.17 | 1 | 0 | 75 | Jared |  | 3.2.1.3 | Jared
1312 | Page Structure Implementation | 07.06.17 | 20.06.17 | 10 | 0 | 2000 | Webster |  | 3.2.2 | Webster
1313 | Create place holders | 06.06.17 | 06.06.17 | 1 | 0 | 200 | Webster |  | 3.2.3 | Webster
1311 | sketch out structure | 02.06.17 | 05.06.17 | 2 | 0 | 400 | Webster |  | 3.2.4 | Webster
454 | CMS (Content Management System) | 21.06.17 | 11.07.17 | 15 | 0 | 3500 | Jared |  | 3.3 | Jared
1323 | User Testing - CMS | 26.06.17 | 10.07.17 | 11 | 0 | 125 |  |  | 3.3.1
1324 | customur use the CMS | 26.06.17 | 26.06.17 | 1 | 0 | 25 | Jared |  | 3.3.1.1 | Jared
1325 | customur use the CMS | 03.07.17 | 03.07.17 | 1 | 0 | 25 | Jared |  | 3.3.1.2 | Jared
1326 | customur use the CMS | 10.07.17 | 10.07.17 | 1 | 0 | 75 | Jared |  | 3.3.1.3 | Jared
1320 | CMS (Content Management System) Implementation | 26.06.17 | 11.07.17 | 12 | 0 | 2400 | Webster |  | 3.3.2 | Webster
1321 | placeholder article and papir protoype | 23.06.17 | 23.06.17 | 1 | 0 | 200 | Webster | 2175 | 3.3.3 | Webster
1322 | CMS research | 21.06.17 | 22.06.17 | 2 | 0 | 400 | Webster |  | 3.3.4 | Webster
1329 | Payment / Ordering system Implementasion Implementation | 12.07.17 | 16.08.17 | 26 | 0 | 1900 |  |  | 3.4
1332 | User Testing - Payment / Ordering System | 17.07.17 | 14.08.17 | 21 | 0 | 300 |  |  | 3.4.1
1333 | Private person buying | 17.07.17 | 17.07.17 | 1 | 0 | 25 | Jared |  | 3.4.1.1 | Jared
1334 | Private person buying | 24.07.17 | 24.07.17 | 1 | 0 | 50 | Jared |  | 3.4.1.2 | Jared
1335 | Business order form | 31.07.17 | 31.07.17 | 1 | 0 | 75 | Jared |  | 3.4.1.3 | Jared
1336 | Store trying to make a order or a agrement | 07.08.17 | 07.08.17 | 1 | 0 | 75 | Jared |  | 3.4.1.4 | Jared
1337 | Extra testing | 14.08.17 | 14.08.17 | 1 | 0 | 75 | Jared |  | 3.4.1.5 | Jared
1330 | Payment / Ordering system Implementasion | 24.07.17 | 16.08.17 | 18 | 0 | 0 |  |  | 3.4.2
1429 | User registration | 14.07.17 | 21.07.17 | 6 | 0 | 1200 | Webster |  | 3.4.3 | Webster
1331 | Payment System Research | 12.07.17 | 13.07.17 | 2 | 0 | 400 | Webster |  | 3.4.4 | Webster
452 | CRM (Customer Relationship Management) | 17.08.17 | 05.09.17 | 14 | 0 | 6700 | Webster |  | 3.5 | Webster
1340 | User Testing - CRM Integration | 28.08.17 | 04.09.17 | 6 | 0 | 100 |  |  | 3.5.1
1341 | Private person integration | 28.08.17 | 28.08.17 | 1 | 0 | 25 | Jared |  | 3.5.1.1 | Jared
1342 | Business ordering integration | 04.09.17 | 04.09.17 | 1 | 0 | 75 | Jared |  | 3.5.1.2 | Jared
1343 | CRM (Customer Relationship Management) Implementation | 23.08.17 | 05.09.17 | 10 | 0 | 2000 | Webster |  | 3.5.2 | Webster
1344 | CRM Resarch | 17.08.17 | 22.08.17 | 4 | 0 | 1800 | Jared |  | 3.5.3 | Jared;Webster
446 | Implement Design | 06.09.17 | 29.09.17 | 18 | 0 | 4350 | Jared | 1859 | 3.6 | Jared
1358 | User Testing - Design Test | 11.09.17 | 25.09.17 | 11 | 0 | 300 |  |  | 3.6.1
1360 | Private person use of the page | 11.09.17 | 11.09.17 | 1 | 0 | 100 | Jared |  | 3.6.1.1 | Jared
1362 | Business use of the page | 18.09.17 | 18.09.17 | 1 | 0 | 100 | Jared |  | 3.6.1.2 | Jared
1444 | Costumor Update Page | 25.09.17 | 25.09.17 | 1 | 0 | 100 | Jared |  | 3.6.1.3 | Jared
458 | Theme Development | 06.09.17 | 29.09.17 | 18 | 0 | 3600 |  |  | 3.6.2
1487 | PHP and Integration | 22.09.17 | 29.09.17 | 6 | 0 | 1200 | Webster |  | 3.6.2.1 | Webster
1488 | JAVASCRIPT and Animations | 14.09.17 | 21.09.17 | 6 | 0 | 1200 | Webster |  | 3.6.2.2 | Webster
1486 | HTML and CSS | 06.09.17 | 13.09.17 | 6 | 0 | 1200 | Webster |  | 3.6.2.3 | Webster
1490 | User Testing - Design and SEO | 29.09.17 | 16.10.17 | 12 | 0 | 650 |  |  | 3.7
1492 | User testing out all functionallity on page | 29.09.17 | 29.09.17 | 1 | 0 | 250 | Jared |  | 3.7.1 | Jared
1504 | User testing out all functionallity on page | 02.10.17 | 02.10.17 | 1 | 0 | 250 | Jared |  | 3.7.2 | Jared
1494 | Test SEO matrics | 09.10.17 | 09.10.17 | 1 | 0 | 100 | Jared |  | 3.7.3 | Jared
1511 | Conduct tests for security | 16.10.17 | 16.10.17 | 1 | 0 | 50 | Jared |  | 3.7.4 | Jared
450 | SEO (Search Engine Optimization) | 02.10.17 | 09.10.17 | 6 | 0 | 1650 | Jared |  | 3.8 | Jared;Webster
449 | Security/Backup System | 10.10.17 | 20.10.17 | 9 | 0 | 1800 | Webster |  | 3.9 | Webster
1521 | Make ready for launch | 23.10.17 | 07.11.17 | 12 | 0 | 2400 | Webster |  | 3.1 | Webster
2081 | Progress Test With Customur | 21.06.17 | 21.06.17 | 0 | 0 | 0 | Jared |  | 3.11 | Jared
202 | Webpage content creation | 20.06.17 | 20.10.17 | 89 | 0 | 23700 |  |  | 4
2165 | Setup | 22.06.17 | 22.06.17 | 1 | 0 | 0 |  |  | 4.1
2080 | Research and sketches | 23.06.17 | 07.07.17 | 11 | 0 | 0 |  |  | 4.2
1536 | Identity elements | 10.07.17 | 05.09.17 | 42 | 0 | 9050 | Jared |  | 4.3 | Jared
1613 | Style Sheet revison 1 | 10.07.17 | 21.07.17 | 10 | 0 | 2000 | Kat |  | 4.3.1 | Kat
2173 | Style Sheet revison 2 | 24.07.17 | 07.08.17 | 11 | 0 | 2200 | Kat |  | 4.3.2 | Kat
1859 | Style and Behavoir Guid Guide | 10.08.17 | 05.09.17 | 19 | 0 | 3800 | Kat |  | 4.3.3 | Kat
2168 | Animtaions | 24.08.17 | 05.09.17 | 9 | 0 | 0 |  |  | 4.3.3.1
2171 | CSS and HTML examples | 10.08.17 | 23.08.17 | 10 | 0 | 0 |  |  | 4.3.3.2
2078 | Style Meeting with customur | 08.08.17 | 08.08.17 | 0 | 0 | 0 | Jared | 1613;2173 | 4.3.4 | Jared;Kat
2175 | Photo content for CMS test articles and for Stylesheet | 20.06.17 | 22.06.17 | 3 | 0 | 1050 | Robin (Photo) |  | 4.4 | Robin (Photo)
2177 | Photos for the product pages | 03.07.17 | 07.07.17 | 5 | 0 | 1750 | Robin (Photo) |  | 4.5 | Robin (Photo)
2270 | Articles and Photos | 06.09.17 | 28.09.17 | 17 | 0 | 9050 | Kat |  | 4.6 | Kat
2272 | Article - About Company | 06.09.17 | 11.09.17 | 4 | 0 | 800 | Kat |  | 4.6.1 | Kat
2273 | Photos - Company | 08.09.17 | 08.09.17 | 1 | 0 | 350 | Robin (Photo) |  | 4.6.2 | Robin (Photo)
2274 | Article - About the Prroduction | 12.09.17 | 15.09.17 | 4 | 0 | 800 | Kat |  | 4.6.3 | Kat
2275 | Photos - Production | 14.09.17 | 14.09.17 | 1 | 0 | 350 | Robin (Photo) |  | 4.6.4 | Robin (Photo)
2276 | Article - Customer stories | 18.09.17 | 21.09.17 | 4 | 0 | 800 | Kat |  | 4.6.5 | Kat
2277 | Photos - Customer stories | 20.09.17 | 20.09.17 | 1 | 0 | 350 | Robin (Photo) |  | 4.6.6 | Robin (Photo)
2278 | Article - Christmas sale | 22.09.17 | 27.09.17 | 4 | 0 | 800 | Kat |  | 4.6.7 | Kat
2279 | Photos - Christmas sale | 25.09.17 | 26.09.17 | 2 | 0 | 700 | Robin (Photo) |  | 4.6.8 | Robin (Photo)
2280 | Photos - Editing | 27.09.17 | 28.09.17 | 2 | 0 | 700 | Robin (Photo) |  | 4.6.9 | Robin (Photo)
2282 | End revision and make ready for launch | 03.10.17 | 20.10.17 | 14 | 0 | 2800 | Kat |  | 4.7 | Kat
1529 | Acceptence try run test | 02.10.17 | 02.10.17 | 0 | 0 | 0 | Jared |  | 5 | Jared
203 | Acceptence test | 09.11.17 | 09.11.17 | 0 | 0 | 0 | Jared |  | 6 | Jared
350 | Handoff / future coaporation | 09.11.17 | 13.11.17 | 3 | 0 | 0 |  | 203 | 7
365 | Hosting and cridentials | 09.11.17 | 09.11.17 | 1 | 0 | 0 |  |  | 7.1
377 | Instruction matirai and training | 09.11.17 | 13.11.17 | 3 | 0 | 0 |  |  | 7.2
417 | Page goes live | 09.11.17 | 09.11.17 | 0 | 0 | 0 |  |  | 7.3
ID | Name | Default role | e-mail | Phone | Assignment role | Standard rate | Note
7 | Jared | Default:1 | jared@rayos.studio | 10 00 10 00 |  | 250
8 | Clark | SoftwareDevelopment:10 | clark@rayos.studio | 20 00 20 00 |  | 400 | Hired in accountent
9 | Webster | SoftwareDevelopment:9 | Webster@Rayos.studio | 30 00 30 00 |  | 200
10 | Kat | SoftwareDevelopment:6 | kat@rayos.studio | 40 00 40 00 |  | 200
11 | Robin (Photo) | Default:0 | robin@take.photo | 50 00 50 00 |  | 350